## Sheet1
PEER REVIEW BUG | SEVERITY | FIXED? | COMPLETED BY | SOLUTION
Towers sometimes don’t shoot enemies when they are in range. | HIGH | YES | Kallan | Scripting for Turret targeting altered to check for null objects. Null objects are purged from target list and the next target is retrieved.
Build slots take priority over tower selection buttons | LOW | N/A | George | Was unable to recreate occurance of bug after change in the UI and the way the player builds. Assumed resolved.
Some build slots don’t look right | LOW | YES | Sean | Turret build locations have been corrected to be fully visible.
Camera can scroll away from the map entirely. | MODERATE | YES | George | The player control has been completely changed to use a mixture of WASD and mouse clicks. All of these issues have been resolved as a result.
Zooming continues after scroll wheel is stopped. | LOW | YES
Zooming operates inverse from expectation. | LOW | YES
It is possible to zoom past the furthest distance out or in, and the scroll amount will still gain an amount making you have to scroll extra to reverse the zoom direction. | LOW | YES
Game camera moves when menu sliders are moved. | LOW | YES
No delay before enemies start spawning | HIGH | YES | Sean | Added a 10 second timer between waves. There is now a delay between waves to give the player time to get organized.
There is no in-game audio. | HIGH | YES | Kallan, George, Sean | Audio has been added.
When Game Over state is reached, game still functions despite on-screen message. | MODERATE | YES | Sean | Game now "slows" after player wins/loses.
“Weakest” turret seems to be most powerful. | MODERATE | YES | Sean | Turret power levels have been tweaked to be more in line with enemy wave and power level.
There is no notification when the player wins like there is with game over. | MODERATE | YES | George | A player win screen has been added if the player succeeds in defeating all 10 waves and the boss.
Game Over Notice overlaps with Options Menu | MINOR | YES | George | Corrected error by turning off other menus when Game Over is displayed.
The levels happen really, really fast. Maybe slow down the progression. The boss appears before two minutes have passed, and I’ve built only about 4 towers by then. With all the tower slots available, you would think you would have a lot of building ahead of you. Basically, it’s really hard for just a first level. Maybe try scaling the difficulty by spreading out enemy waves earlier on before ramping it up at the end? |  | KINDA | Sean | Tweaked the way the waves so they should be less difficult in the beginning but the player has to use some strategy which is why money isn't plentiful and enemies get stronger.
Maybe gain money faster or make the enemies a little slower. You can only buy a few towers with your starting money and loose before being able to buy more than two more. |  | YES | Sean | Enemies are worth slightly more.
Add retry button to game over screen |  | YES | George | There is now a replay button on the gameover screen.
Put slightly transparent panel background behind credits to make them easier to see |  | YES | Sean | Put a different image behind scoring area.
Add sound effects: spawning sound, tower sounds, creature sounds, attacking sounds, background music. |  | YES | Kallan, George, Sean | There is now sound.
Add more detail or color to the game environment, ex: more than one terrain texture like sand by the water, burnt texture by crash |  | YES | Sean | Overhauled the entire terrain.
Mouse scroll zoom is really sluggish and a bit impractical. Can it be sped up? |  | YES | George | Zoom now works better and in the correct axis.
“Build” Button seems to be redundant. Maybe just have the turret icons become directly clickable as they become available for purchase? |  | YES | George | Turrets are now able to be built once you have the money without needing a build button.
Title screen seems to have the wrong title. |  | YES | George | Correct title now displays.
INSTRUCTOR BUG / SUGGESTIONS | SEVERITY | FIXED? | COMPLETED BY | SOLUTION
I would look into making the asdw keys move the camera around. |  | YES | George | This suggestion was already in the works and has been implemented into this build.
moving around the playing field was difficult. maybe speed up the movement a little bit. I was doing mulitple things on my computer... so maybe that was slowing it down. that was it... I went back into the game and it ran better. |  | YES | George | Player movement controls were sluggish, these have been sped up and the actual controls have been changed.
Myabe having a popup of info when you hover over or select one of the build items to help describe what they do. |  | N/A |  | This is something that will be implemented if time allows.
the weapons seem to be out of preportions to the bad guys. I would say, either make the weapon models smaller or make the bad guys bigger. |  | YES | KALLAN | Adjusted the scale of enemies and turrets to make them more inline.
Mini-map was a little to light.. hard to see. |  | YES | SEAN | Added a background to the mini-map.
I would try to make the mini-map usable... see bad guys... be able to click on it and move to that location. |  | N/A |  | This is something that will be implemented if time allows.
water look nice but to calm. maybe adding some rocks to the water or a water fall/rapids to it might help. |  | YES | SEAN | A waterfall and rock was added but other changes will only come if time allows.
every once in a while a rocket will shoot out into outerspace. I assume that the original target that the rocket was for was destroyed. |  | YES | KALLAN | Has a timed destruction script, rocket will still fly off to nowhere but will destroy itself in a few seconds.
zoom scroll wheel is backwards. when I want to zoom out, I have to scroll in and vise versa. |  | YES | GEORGE | This has been fixed with the new control reworking.
game seems a little lagy when there is allot of stuff going on. |  | NO |  | Reduction in resource draw is being considered and accomplished where possible.
Title menu screen... not sure what the picture is suppose to be. |  | YES | GEORGE | Screen correctly shows the current game build rather than the old game build.
shots out of the weapons are not coming out of the mussle. |  | YES | KALLAN | Shots now correctly shoot from the muzzle of the laser turret.
at one point I was done with wave 6 and the game would not send the next wave. |  | YES | SEAN | There was an error with the way enemies were counted/removed. A check for active enemies was needed.
are the weapons upgradeable? |  | NO |  | This is being considered and will be in final build if possible.
can I delete a weapon once it has been placed on the playing field? |  | YES | KALLAN | There is now a SELL button next to the turrets. You click that and then click a turret to sell it.
UPDATED: 10:40PM